## Slide 1
Delivery Status — SIF & APIM HLD
Leadership update · Week 6 of 8 · 29 Sep 2026
ON TRACK
1 week ahead
SIF completed in Week 3 vs. a Week 4 plan
All reviews done
SIF Document ratified with Chaucer stakeholders
APIM in review
HLD started early (Wk 4) - internal review now
DELIVERY TIMELINE · 8 WEEKS
Complete
In review
Upcoming
Wk 1
Wk 2
Wk 3
Wk 4
Wk 5
Wk 6
Wk 7
Wk 8
SIF — complete (Wk 3)
APIM HLD - internal review
Joint review · TDA · Wrap-up
Now · Wk 6
SIF — Systems Integration Framework
Part 1
COMPLETE
Framework, reference architecture & pattern catalogue finalised
Decision-guidance model & Data Platform interface boundary documented
Peer-reviewed with Chaucer Architects content review-ready
NEXT TDA submission pushed as planned due to availability of Steve Coldwell.
APIM — High-Level Design
Part 2
IN REVIEW
Edge Service and APIM SKU- Tier Desing Decision Confirmed with Chaucer Security and Cloud Architect.
Observability, throttling/caching & Dev/UAT/Prod strategy drafted
Started in Week 4 ahead of the planned Wk 4–6 window
NEXT Complete internal review → joint review with Chaucer → consolidate for TDA.
WATCH · SIF TDA sign-off
Owner: Chaucer - awaiting had a meeting with stakeholder yesterday. SIF content is complete and ready to be shared with TDA, so no rework is expected.
LOOK-AHEAD · NEXT MILESTONES
Wk 6 APIM HLD internal review Wk 7 APIM HLD familiarization with Chaucer Wider Audience
Wk 8 APIM HLD TDA submission & wrap-up
© 2026–2027 Cognizant | Private
1