## Slide 1
Estimated time to implement
indicative
A phased plan for Option 1, with Option 2 as a later evolution. Phases overlap; ranges reflect scope and vendor readiness.
0
1
2
3
4
5
6
7
8
9
months →
Discovery & design
~1 mo
API contract, environments, security model
Core platform build
~2 mo
APIM, Repair + WO APIs, receiver, Service Bus, handler
Adapters & pilot vendors
~1.5 mo
Per-channel adapters; onboard 2-3 pilot vendors
Observability & resilience
~1.5 mo
Monitoring, retry, dead-letter, alerts, hardening
Vendor rollout (config)
~2 mo
Onboard remaining vendors as configuration
Option 2 evolution (later)
evolution phase
Option 1 — roughly 3 to 5 months to first value
3-5 mo
Option 1 to first value
+4 mo
Option 2 evolution, later
config
each extra vendor after launch
Indicative only: assumes a small dedicated team and reasonable vendor responsiveness. Exact timing and phase overlap firm up after discovery.