## Slide 1: Systems Integration Framework & APIM High-Level Design
July 17th, 2026
1

## Slide 2
Executive Summary
Cognizant Microsoft Integration Capabilities
Engagement Scope
Case Studies
Delivery Approach & Methodology
High-Level Delivery Plan
Resource Plan
Q&A
Agenda

## Slide 3
Chaucer’s enterprise transformation requires integration to become a strategic enabler of automation, straight-through processing, and scalable connectivity. Current integration approaches vary across the application and vendor estate, creating an opportunity to establish a cohesive enterprise Systems Integration Framework (SIF) that promotes reuse, loose coupling, and cloud-native services.
Executive Summary​
Cognizant proposes to work in close collaboration with Chaucer's lead Enterprise Architect to define, document and review the System Integration framework(SIF) — aligned to Chaucer's cloud and data operating model — grounded in Service-Oriented Architecture (SOA) principles rather than a microservices model, together with a High-Level Design (HLD) for Azure API Management (APIM) as the enterprise's single API ingress point.
This engagement is focused on architecture and governance clarity — the expectation is SME collaboration and review with Chaucer's lead Architect, with design decisions and rationale captured — not simply tool selection or wholesale platform redesign, nor a redefinition of Chaucer's cloud strategy. Cognizant brings relevant Azure integration delivery experience to this engagement, informing the practical patterns and delivery approach proposed here, and will produce peer-reviewed artefacts for publication to Chaucer's Technical Design Authority (TDA) as a shared responsibility between both parties.
Cognizant proposes to deliver this engagement over an 8-week timeline, using an onsite/offshore delivery model that leverages the existing knowledge Cognizant's in-place onsite and offshore resources already hold of Chaucer's environment, supplemented by the net addition of one offshore Lead Integration Architect to complete the Architecture define phase.

## Slide 4: Microsoft Azure API / Integration Capabilities
Disclaimer: All Trademarks & Registered Trademarks are the property of their respective owners
Servicing Global Clients & Providing Innovative Industry Solutions for 14+ Years
Gold Application Integration Partner
Application Integration Partner of the Year Award Finalist
100+ Microsoft Customers
350+ MS Integration Projects in 12 Years
500+ Product Experts
450+ Certified Associates
5+ Gen AI Solutions & Accelerators
  Single integration platform for customer e-commerce segments and worldwide order management system to create a holistic Omni-channel environment
  Created a remarkable Digital Experience that captures guest’s imagination for largest operator of world largest theme park
  Enterprise integration gateway platform for its assessment operating system and other enterprise infrastructures
Indicative Benefits’ Snapshot
Azure Integration Services (iPaaS)
Azure Logic Apps, Azure Service Bus, Azure Event Grid
Azure API Management, API Center
Azure Data Factory, Azure Event Hub
Azure API Apps, Azure Functions
Microservices on Azure
Azure Kubernetes Service (AKS), Azure Container Instances (ACI), Azure Service Fabric, Service Fabric Mesh
.NET Core, ASP.NET Web API, WCF
BizTalk Server 2006 to 2020 & ESB Tool kit
AIS Design Generator
Agentic AI based Azure Integration services design generator which creates AIS design document from BizTalk, MuleSoft, Tibco and Layer 7 artefacts. Reduces manual effort for design and development for migration activities.
BizTalk Document Generator
AI based BizTalk documentation tool which generated BizTalk documentation from BizTalk artefacts Improves analysis and reverse engineering productivity.
Azure Design & Development Pacer Kit
Provides components which are commonly used by Azure iPaaS development time. Improves design & development productivity by 10%-15%
Disclaimer: All Trademarks & Registered Trademarks are the property of their respective owners
Technology Specializations
Accelerators And Solutions
© 2026–2027 Cognizant | Private

## Slide 5: Engagement Scope

## Slide 6
Scope of Engagement
Documented Systems Integration Framework covering synchronous, asynchronous, webhook and orchestration patterns.
Reference architecture aligned to Azure integration services: API Management, Logic Apps, Service Bus, Event Grid, Event Hub, Azure Functions, and Azure Data Factory
Integration pattern catalogue with worked examples and a decision guidance model (API vs. event vs. orchestration vs data pipeline).
Security and operations principles at the framework level: use of Managed Identity, Azure Key Vault for secrets, source control/CI-CD expectations, and monitoring/observability principles for integration assets.
Guardrails, exception-handling process, and Data Platform (Snowflake) interface boundary.
Facilitated SME sessions with Chaucer Architects to define, review and ratify the framework collaboratively
In Scope – SIF (Part 1)
API discovery/consumption model (developer portal)
Authentication and authorization approach using Azure Entra ID and OAuth 2.0.
Logical access model for private/public endpoints across VNETs, Azure PaaS and SaaS.
HLD-level protection guidance (OWASP API Top 10, DDoS), HA design concept and DR considerations.
API versioning/lifecycle approach and observability & policy design (logging, throttling, caching).
Traffic management concepts, components and Dev/UAT/Prod environment strategy recommendation.
In Scope – APIM HLD (Part 2)

## Slide 7
Infrastructure
Design, configuration or deployment of network architecture, firewalls, load balancers, VPN/ExpressRoute, or VNet topology.
Physical/technical implementation of Disaster Recovery (DR) and business continuity solutions.
Provisioning, deployment or configuration of Azure PaaS, IaaS or SaaS components (e.g. standing up APIM, Logic Apps, Function Apps, Service Bus namespaces, Landing Zones, subscriptions).
Configuration of WAF, DDoS protection services, or network security groups.
Data Platform
Design or build of the Snowflake data integration/ingestion framework, ETL/ELT pipelines, or data models.
Any Snowflake platform administration, performance tuning, or licensing activity.
Other Exclusions
Production or wholesale redesign of a generic SOA/integration manual not tailored to Chaucer.
Tool or vendor comparison/selection exercises.
Redefinition of Chaucer’s broader cloud strategy.
Adoption or design of a microservices architecture model.
Build, coding or unit testing of APIs, Logic Apps workflows, or Azure Functions (this engagement produces framework, patterns and HLD, not working code).
Migration of existing point-to-point integrations to the new framework (a candidate follow-on phase, not included here).
Penetration testing, security control testing, or formal security accreditation activity.
End-user or developer training/enablement delivery beyond walkthroughs of the delivered artefacts.
Ongoing run/support, or production go-live activity following publication of the artefacts.
Software licensing procurement or commercial negotiation with Microsoft or third parties.
Out of Scope

## Slide 8: Case Studies

## Slide 9
Case Study – Digital Transformation
Client Profile - Client is a global maritime logistics and shipping conglomerate whose Ocean, Corporate, Terminal and Land Transport businesses rely on a legacy TIBCO-based integration landscape to exchange data with internal applications and 60+ trading partners.
Client Requirements
Build a unified, API-led integration framework to standardize how internal applications (A2A) and external trading partners (B2B) exchange business data.
Provide a single, governed gateway for all inbound and outbound transactions with strong authentication, traffic control and threat protection.
Migrate legacy TIBCO BusinessConnect / BusinessWorks integration flows to a scalable, cloud-native platform.
Expose data to consuming applications in standardized business/process JSON payloads regardless of source protocol.
Ensure end-to-end observability, logging and proactive alerting across every API and integration flow.
Cognizant Solution
Implemented Azure API Management (APIM) as the unified API gateway fronting all inbound/outbound partner (B2B) and application (A2A) traffic.
Built a wrapper service using Azure Logic Apps and Azure Functions, integrating with VLTrader/SFTP file shares and transforming payloads to standardized JSON before publishing through APIM.
  Azure API Management
  Azure Logic Apps
  Azure Functions
  Service Bus
  Integration Account
  Key Vault, Storage Account, Azure Monitor, Entra ID
Enforced API policies for OAuth 2.0 / certificate-based security, content-based routing and traffic throttling across products.
Enabled end-to-end monitoring using Log Analytics, Application Insights and Azure Monitor, with automated alerts for failures..
Key Benefits
Centralized, secure API gateway improving governance and control.
Standardized, reusable integration framework reducing effort to onboard new interfaces.
Improved scalability and resilience with serverless, Azure-native components.
Faster partner/application onboarding through a self-service API catalog.
End-to-end visibility with proactive monitoring and alerting.
Reduced operational cost via pay-per-use pricing model.

## Slide 10
Client Requirements
Publishing APIs for external/internal developers to discover, learn, and consume.
Providing interactive API documentation (Swagger/Open API) and code samples.
Managing API keys, subscriptions, and access for developers.
Enabling self-service onboarding for developers & Management approvals.
API Testing
Sharing announcements, guides, and support resources.
Integrating with external systems (e.g., support, analytics)
Managing user roles and access
Integrate AI-powered chatbots for instant support and API guidance.
Add AI-based personalization for portal content and onboarding.
Case Study – Unified Developer Portal
Cognizant Solution
Key Benefits
Azure API Management (APIM) lifecycle management and establishing API C4E (Center for enablement).
Focusses on the findability aspects of APIs for developers by integrating with http://xxx, and centrally managed security controls, eliminating the duplication of APIs.
The UI portal[Developer Portal] offers comprehensive search functionality, allowing users to efficiently locate APIs, products, and tags, enhancing the discoverability and accessibility of resources.
It integrates with GenAI platform, providing advanced interaction capabilities and leveraging AI-driven insights to optimize user experience and enterprise engagement
Extract the APIM metadata from multiple APIM instances, stored in Azure Blob storage, consolidated, and indexed through RAG model into the Azure AI Search Service to enable chatbot integration within the Developer Portal.
The normalized metadata exposed as REST API
The UI designed and developed in Microsoft Power Apps
The Data loaded into Dataverse table using Power Automate flows & Rest APIs.
Power connectors used for API testing invoking APIM's APIs.
Azure Functions, Logic App, Python, ADO, Power Platform, APIM, Azure AI service.
Client Profile - An international organization of five institutions that provides financing, policy advice, and technical assistance to developing countries to reduce poverty and boost shared prosperity.

## Slide 11: Delivery Approach & Delivery Plan

## Slide 12
Delivery Approach & Methodology
  Review existing documentation, current integration landscape, and prior architectural decisions
  Run structured interviews with Chaucer stakeholders and existing Cognizant Team.
  Confirm scope boundaries, especially the interfaces to infrastructure and data-platform workstreams.
  Develop draft framework structures, principles, reference architecture and pattern catalogue in working sessions with Chaucer's Architect, capturing design decisions and rationale as they are agreed.
  Consolidate agreed content into the formal SIF and APIM HLD artefacts, reference diagrams and decision-guidance material, peer-reviewed by both Cognizant and Chaucer.
Walk the artefacts through Chaucer's TDA governance forum and support formal publication as a shared Cognizant/Chaucer output.
Discover
Define
Validate
Document
Publish
  Test draft patterns and the APIM HLD against representative current/planned integration scenarios provided by Chaucer, refining guidance so it is actionable rather than theoretical.

## Slide 13
Indicative timeline
Eight weeks, phased with deliberate overlap
Wk 1
Wk 2
Wk 3
Wk 4
Wk 5
Wk 6
Wk 7
Wk 8
Wk 9
Mobilization & Discovery
SIF core (framework + architecture)
APIM High level Design
Joint Review
Finalization - TDA Submission
& Wrap up
M1
M2
M3
*Milestones: M1 SIF core baseline · M2 : APIM Design baseline · M3 consolidated framework published to TDA. ** Future phase of implementation follows from Week-9 subjected to agreement on next phase
© 2026–2027 Cognizant | Private
7
Implementation

## Slide 14
Stage | Timing | Key Activities | Key Outputs
0. Mobilization & Discovery | Week 1 | • Kick-off and engagement governance agreed • Access, contacts and document requests confirmed • Review Cloud & Data operating model, current integration landscape and standards, landing zone details • Stakeholder interviews to confirm scope boundary with infra/data workstreams and security considerations | Mobilization pack; RAID log opened; current-state summary; validated scope boundary
1. SIF Definition | Weeks 2–4 | • Joint working sessions on principles, patterns, decision guidance • Draft reference architecture diagrams • Draft data-platform guardrails | Draft SIF v0.x; pattern catalogue; decision guidance
2. APIM High-Level Design | Weeks 4–6 | • Design security/auth, HA, versioning, observability, environment strategy • Traffic management concept | Draft APIM HLD
3. Joint Review & Iteration | Weeks 4 &7 (overlay) | • Structured review with Chaucer Architects • Scenario validation | Reviewed, iterated artefacts
4. Finalisation & TDA Publication | Weeks 5 & 8 | • Finalise artefacts • Publish to TDA, walkthrough and sign-off support. • Phase –2 Scope – Planning and Cost Analysis | Final SIF; Final APIM HLD; TDA submission, Phase -2 Implementation Timelines and Cost
High-Level Delivery Plan

## Slide 15: Resource Plan

## Slide 16
Team and resource model
A lean blended team (Hybrid)
Role | Name | Location | Allocation Type | Primary focus
Lead Integration Architect | TBC | Offshore | New | Design authority; pairs with Chaucer's architect; owns SIF direction, Governance, sets Pattern catalogue, APIM high-level design, Reference diagrams
Azure / APIM Architect | Joycell Sundararaj (Joycell.Sundararaj@cognizant.com) | Onshore | Existing | Pattern catalogue, APIM design and overall documentation, peer & Architect review, and TDA alignment
Offshore Lead | Pragyan Tripathy (Pragyanparamita.tripathy@cognizant.com) | Offshore | Existing | Manages over all reporting delivery of Project
 |  |  |  | 8-weeks engagement
8
*Cost : £13k (Approx)

## Slide 17: Q & A ?

## Slide 18: Appendix​

## Slide 19
1
Chaucer provides a dedicated lead Enterprise/Integration Architect as the primary counterpart throughout the engagement.
2
Chaucer’s cloud and data operating model is available at or before kick-off and remains materially stable; changes go through change control.
3
Where not yet documented, Chaucer’s lead Architect will articulate current/target-state principles during Discovery workshops.
4
Chaucer provides existing architecture documentation, integration inventory & standards and existing landing zones details within 5 business days of kick-off.
5
An Azure landing zone, core subscriptions and networking foundations are assumed provisioned under a separate workstream.
6
Snowflake data platform is an existing or separately delivered capability; this engagement defines only the interface/guardrails.
7
Chaucer stakeholders review draft artefacts and provide consolidated feedback within an agreed turnaround (proposed 3 business days).
8
Chaucer’s TDA process, submission format and governance cadence will be shared with Cognizant at kick-off but will be owned by Chaucer
9
No dedicated Chaucer development/test environment is required, as this is a design and documentation activity.
10
Relevant regulatory, compliance and information-security policies will be shared by Chaucer at the outset.
Assumptions

## Slide 20
Dependencies
# | Dependency | Owner | Required By | Impact if not met
1 | Chaucer's Cloud and Data Operating Model — the foundational basis the SIF is required to align to | Chaucer | Week 1 | Without it, the SIF would be built on assumed rather than actual target-state principles, risking rework and misalignment with Chaucer's broader cloud/data strategy
2 | Nomination and ongoing availability of Chaucer Architects for joint design sessions and decision-making | Chaucer | Confirmed at kick-off (Week 1); available throughout Weeks 1–8 | Delays to SIF/APIM design decisions and overall schedule
3 | Access to current-state architecture documentation, integration inventory & application landscape and existing landing zones details | Chaucer | Within 5 business days of kick-off (by Week 1) | Rework of assumptions; slower discovery phase
4 | Access to Chaucer’s templates for documentation | Chaucer | Access confirmed by Week 1 | Delayed documentation work
5 | Coordination with the Chaucer infrastructure workstream on network, DR and PaaS provisioning items referenced by the SIF/APIM HLD | Chaucer | Weeks 2–4; maintained through | Inconsistent assumptions between framework and underlying infrastructure
6 | Coordination with the Data Platform (Snowflake) team on SIF-to-data-platform guardrails | Chaucer / Data Platform team | Week 3 | Ambiguous or unusable data-integration boundary guidance
7 | Stakeholder availability for workshops, interviews and review cycles | Chaucer | Ongoing, Weeks 1–8 | Extended timeline; incomplete validation
8 | Timely decisions on open architectural questions raised during the engagement | Chaucer | Within 3 business days of each item being raised | Schedule slippage; artefacts issued with open items
9 | Confirmation of Chaucer's existing security/compliance policies relevant to integration and API design | Chaucer | Week 2 | Rework of security-related design guidance

## Slide 21
Deliverable | Cognizant Architects | Chaucer Architects | TDA | Infra / Data Workstreams
Systems Integration Framework | R / A | C / A | I | C
Reference Architecture Diagrams | R | C / A | I | C
Pattern Catalogue & Decision Guidance | R | C / A | I | I
Overall Guardrails & Exception Process | R | C / A | I | I
APIM High-Level Design | R | A | I | C
Data Platform Guardrails (SIF boundary) | R | A | I | C (Data Platform)
TDA Submission & Publication | C | R / A | A | I
Deliverables & RACI
R = Responsible, A = Accountable, C = Consulted, I = Informed. All artefacts are peer-produced and reviewed jointly by Cognizant and Chaucer Architects. Final RACI to be confirmed during mobilization.

## Slide 22
Indicative Profile – Lead Integration Architect
LA
Lead Integration Architect
Indicative Profile · Offshore
Azure Cloud-Native
Solution Architecture
Azure Integration (AIS)
API Management (APIM)
Event-Driven Design
API-First Design
Service Bus & Event Grid
Logic Apps, Functions & ADF
Legacy Modernization
Solution Governance
DevOps & IaC
AI Accelerators
PROFILE
Senior Azure Architect with 18+ years in enterprise IT, specializing in solution architecture and hands-on delivery of Azure cloud-native and Azure Integration Services (AIS) platforms — with API Management (APIM) as a core focus. Designs API-first, event-driven solutions and reference architectures, and establishes solution governance, guardrails, HA/DR and cost optimization for scalable, resilient delivery.
CORE CAPABILITIES
Azure Integration Platform (AIS + APIM + ADF): Designs and builds enterprise integration platforms on Azure Integration Services - APIM gateways, Service Bus, Event Grid/Hub and Logic Apps/Functions — standardizing API-first, event-driven delivery across teams.
APIM Gateway & Governance Framework: Establishes reusable API Management patterns for OAuth2/JWT security, throttling, versioning, product/subscription models and developer-portal publishing, adopted as engagement-wide standards.
Event-Driven Integration Backbone: Architects pub-sub and message-routing solutions on Service Bus and Event Grid/Hub, applying claim-check, competing-consumers, retry and dead-letter patterns for resilient, decoupled systems.
Legacy-to-Azure Modernization: Leads feasibility assessments, reference architectures and solution shaping to transition complex legacy middleware landscapes to scalable Azure PaaS.
AI-Assisted Engineering: Applies AI-driven / agentic engineering accelerators to generate reusable integration assets, improving delivery velocity and prototyping.
Observability & Resilience: Implements observability practices (dashboards & insights) and embeds HA/DR and cloud cost optimization across solutions.
Architecture Guardrails & Governance: Establishes solution design frameworks and guardrails for consistent, scalable delivery; mentors engineers and aligns cross-functional integration strategy.
INDICATIVE QUALIFICATIONS/ CERTIFICATIONS
Microsoft Certified: Azure Solutions Architect Expert
Microsoft Certified: Azure Developer Associate