## Summary
MuleSoft Exit-Replan vs Prod Inventory: Gap Analysis
HEADLINE NUMBERS
Metric | Count
Integrations reviewed (50 prod + 2 replan-only) | 52
Covered in replan (In Replan = Yes) | 29
NOT in replan (any disposition) | 23
-> TRUE GAPS (live in prod, not out-of-scope) | 10
-> OOS-tagged in prod but ACTIVE (no replan owner) | 3
-> OOS-tagged in prod (confirm + document in replan) | 5
-> Zero prod footprint (likely alias / dedupe) | 5
High priority (in Gap Register) | 3
Medium priority (in Gap Register) | 12
Unmapped live prod apps (see Unmapped_Prod_Apps) | 13
DISPOSITION LEGEND
Disposition | Meaning | Typical priority
TRUE GAP - live in prod, absent from replan | Started app(s) and/or enabled scheduler(s), NOT flagged out-of-scope anywhere, and no matching replan line. Must be dispositioned into the plan now. | High/Med
Prod-tagged OOS but STILL ACTIVE | Prod file marks it Out of Scope, yet it still has ENABLED schedulers running. Contradiction: confirm decommission owner & date, or bring into plan. | Med
Prod-tagged Out of Scope | Prod file marks Out of Scope; replan has no explicit line or confirmation trail. Add an explicit OOS row with sign-off for auditability. | Low
Zero prod footprint - alias/dedupe | Exists only as a name in the integration map (0 started apps, 0 triggers). Likely an alias/duplicate of another integration or already decommissioned. Confirm & dedupe. | Low
In replan | Present in MS_exit_replan (in-scope or explicitly dispositioned). No action beyond existing plan. | -

## Gap_Register
Gap Register — every prod integration vs replan (sorted: High → Low)
Integration | In Replan? | Replan Status | Prod Started Apps | Prod Undeployed Apps | Enabled Triggers | Disabled Triggers | Prod File Comment | Disposition | Priority | Recommended Action
MUL-BACS-FILES | No | - | 1 | 0 | 0 | 4 |  | TRUE GAP - live in prod, absent from replan | High | Live in prod (1 started app(s), 0 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it.
MUL-DATALAKE | No | - | 1 | 1 | 3 | 8 | Covered elsewhere | TRUE GAP - live in prod, absent from replan | High | Live in prod (1 started app(s), 3 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it. Prod comment says partly covered under another integration — confirm scope overlap so it is not dropped.
MUL-TRUECOMMERCE | No | - | 3 | 0 | 6 | 10 | UAT pending | TRUE GAP - live in prod, absent from replan | High | Live in prod (3 started app(s), 6 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it. Prod comment flags UAT still pending.
MUL-COLUMBUSFILES | No | - | 2 | 0 | 0 | 0 | UAT pending | TRUE GAP - live in prod, absent from replan | Medium | Live in prod (2 started app(s), 0 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it. Prod comment flags UAT still pending.
MUL-DISTRIBUTIONCENTRE | No | - | 1 | 0 | 0 | 0 |  | TRUE GAP - live in prod, absent from replan | Medium | Live in prod (1 started app(s), 0 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it.
MUL-ECOMM-PRODUCTFEED | No | - | 1 | 0 | 0 | 0 |  | TRUE GAP - live in prod, absent from replan | Medium | Live in prod (1 started app(s), 0 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it.
MUL-ERP-3RD-PARTY | No | - | 2 | 0 | 1 | 16 | Out of Scope | Prod-tagged OOS but STILL ACTIVE | Medium | Prod marks OOS yet 1 scheduler(s) still ENABLED (2 started app(s)). Confirm who owns switch-off and target date; if it must run past Mule exit, pull into plan.
MUL-ICERTIS | No | - | 3 | 0 | 4 | 13 | Out of Scope | Prod-tagged OOS but STILL ACTIVE | Medium | Prod marks OOS yet 4 scheduler(s) still ENABLED (3 started app(s)). Confirm who owns switch-off and target date; if it must run past Mule exit, pull into plan.
MUL-LABLEFILES | No | - | 1 | 0 | 0 | 0 |  | TRUE GAP - live in prod, absent from replan | Medium | Live in prod (1 started app(s), 0 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it.
MUL-MINSTER-NEW-ACCS | No | - | 1 | 0 | 2 | 0 | Out of Scope | Prod-tagged OOS but STILL ACTIVE | Medium | Prod marks OOS yet 2 scheduler(s) still ENABLED (1 started app(s)). Confirm who owns switch-off and target date; if it must run past Mule exit, pull into plan.
MUL-SUPPLIER-PO | No | - | 1 | 0 | 0 | 0 | UAT pending | TRUE GAP - live in prod, absent from replan | Medium | Live in prod (1 started app(s), 0 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it. Prod comment flags UAT still pending.
MUL-SWISSPOST | No | - | 1 | 0 | 0 | 0 |  | TRUE GAP - live in prod, absent from replan | Medium | Live in prod (1 started app(s), 0 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it.
MUL-TIMBERDATABASE | No | - | 2 | 0 | 0 | 3 | UAT pending | TRUE GAP - live in prod, absent from replan | Medium | Live in prod (2 started app(s), 0 enabled scheduler(s)) but NOT in the replan and NOT flagged out-of-scope. Add to MS_exit_replan (or confirm OOS with sign-off) and estimate/resource it. Prod comment flags UAT still pending.
MUL-BRINGG | No | - | 0 | 0 | 0 | 0 | Out of Scope | Prod-tagged Out of Scope | Low | Prod marks Out of Scope. Add an explicit OOS row to the replan with named sign-off (replan currently has no confirmation trail for this one).
MUL-CHEVIN-TO-TRAKM8 | No | - | 1 | 0 | 0 | 0 | Out of Scope | Prod-tagged Out of Scope | Low | Prod marks Out of Scope. Add an explicit OOS row to the replan with named sign-off (replan currently has no confirmation trail for this one).
MUL-COLUMBUSDOCS | No | - | 0 | 0 | 0 | 0 |  | Zero prod footprint - alias/dedupe | Low | No started apps or triggers — exists only as a label in the integration map. Likely an alias/duplicate of an in-scope integration or already decommissioned. Confirm and dedupe.
MUL-CUSTOMER-EDI | No | - | 0 | 0 | 0 | 0 |  | Zero prod footprint - alias/dedupe | Low | No started apps or triggers — exists only as a label in the integration map. Likely an alias/duplicate of an in-scope integration or already decommissioned. Confirm and dedupe.
MUL-EXPERIAN | No | - | 0 | 0 | 0 | 0 | Out of Scope | Prod-tagged Out of Scope | Low | Prod marks Out of Scope. Add an explicit OOS row to the replan with named sign-off (replan currently has no confirmation trail for this one).
MUL-HYBRIS-CUSTOMER-DOCS | No | - | 0 | 0 | 0 | 0 | Out of Scope | Prod-tagged Out of Scope | Low | Prod marks Out of Scope. Add an explicit OOS row to the replan with named sign-off (replan currently has no confirmation trail for this one).
MUL-ICON-TIMBER-PO | No | - | 0 | 0 | 0 | 0 |  | Zero prod footprint - alias/dedupe | Low | No started apps or triggers — exists only as a label in the integration map. Likely an alias/duplicate of an in-scope integration or already decommissioned. Confirm and dedupe.
MUL-PHOCAS-CREDITCONTROL | No | - | 0 | 0 | 0 | 0 |  | Zero prod footprint - alias/dedupe | Low | No started apps or triggers — exists only as a label in the integration map. Likely an alias/duplicate of an in-scope integration or already decommissioned. Confirm and dedupe.
MUL-PHOCAS-DAILYDATA | No | - | 0 | 0 | 0 | 0 |  | Zero prod footprint - alias/dedupe | Low | No started apps or triggers — exists only as a label in the integration map. Likely an alias/duplicate of an in-scope integration or already decommissioned. Confirm and dedupe.
MUL-SUPPLIER-OCR | No | - | 2 | 0 | 0 | 1 | Out of Scope | Prod-tagged Out of Scope | Low | Prod marks Out of Scope. Add an explicit OOS row to the replan with named sign-off (replan currently has no confirmation trail for this one).
MUL-FTP-DOWNLOADS | Yes | In-scope (active) | 0 | 0 | 0 | 0 | No prod match found | In replan | Medium | In replan with effort/resources assigned, but no prod integration or app matches this name. Reconcile the name to an actual prod app/integration (or confirm it is a new build).
MUL-REDFLAG | Yes | In-scope (active) | 1 | 0 | 0 | 0 | Mapped N/A in prod file | In replan | Medium | In replan and running in prod as starkuk-live-redflag-sapi-v1, but that app is tagged N/A in the prod Integration column. Fix the prod mapping so it is not lost from inventory reports.
MUL-ACCOUNT-VALIDATION | Yes | Special: marked undeployed | 3 | 2 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-BRANCHFINDER | Yes | In-scope (active) | 3 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-COLUMBUS-DOC-HYBRIS | Yes | In-scope (active) | 2 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-COLUMBUS-DOCUMENTS | Yes | Special: Phase-1 / covered | 1 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-CONCUR | Yes | In-scope (active) | 3 | 0 | 1 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-CONSENT | Yes | Special: OOS (confirmed) | 5 | 0 | 1 | 0 | Out of Scope | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-CONSOLIDATEDINVOICE | Yes | In-scope (active) | 7 | 0 | 9 | 10 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-CONSXREF | Yes | In-scope (active) | 0 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-CUSTORDERVALIDATION | Yes | In-scope (active) | 4 | 0 | 3 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-DIGITALASSET | Yes | In-scope (active) | 3 | 0 | 2 | 2 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-FLEETWAVE-ICON-COGNITO | Yes | In-scope (active) | 3 | 0 | 4 | 0 | UAT pending | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-ICONACCOUNTS | Yes | In-scope (active) | 1 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-INBOUND-QUOTES | Yes | In-scope (active) | 2 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-INVENTORYAUTOMATION | Yes | In-scope (active) | 2 | 1 | 6 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-OKTA-SYNC | Yes | Special: OPEN (to check) | 5 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-OPCARDS | Yes | In-scope (active) | 1 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-PRODUCT-CLASSIFICATION | Yes | In-scope (active) | 1 | 1 | 1 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-PRODUCT-FEED | Yes | In-scope (active) | 5 | 0 | 6 | 1 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-PRODUCTS | Yes | In-scope (active) | 3 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-PUNCHOUT | Yes | In-scope (active) | 3 | 0 | 1 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-SALES-PIPELINE | Yes | In-scope (active) | 3 | 0 | 1 | 2 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-SALESORDERS | Yes | In-scope (active) | 3 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-SMS-RELAY | Yes | In-scope (active) | 2 | 0 | 0 | 0 |  | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-SWIFT6-TRANSPORT | Yes | Special: OOS (confirmed) | 1 | 0 | 0 | 0 | Out of Scope | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-TIMBERSUPPLIERS | Yes | In-scope (active) | 1 | 0 | 0 | 0 | UAT pending | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-TRIPDATA | Yes | Special: OOS (confirmed) | 1 | 0 | 0 | 0 | Out of Scope | In replan | - | Covered by existing plan. No new action (see replan for stage status).
MUL-VANSTOCK-PURCHASEORDER | Yes | Special: OOS (confirmed) | 3 | 0 | 0 | 0 | Out of Scope | In replan | - | Covered by existing plan. No new action (see replan for stage status).

## Unmapped_Prod_Apps
Unmapped Prod Apps (Integration = N/A) invisible to integration-level planning
These live prod apps have NO integration mapping, so they do not appear in the Gap_Register or the replan. The order-processing and OAuth items are the ones to act on first.
MuleSoft App | Prod Status | Enabled Triggers | Category | Priority | Recommended Action
sgbd-mule-oauth-provider | Started | 0 | Platform — security | High | Shared OAuth provider. Appears as a dependency under API integrations being migrated (e.g. COLUMBUS-DOC-HYBRIS, ECOMM-PRODUCTFEED). Cross-cutting: must be re-platformed/replaced or every migrated API breaks. Add as an explicit dependency.
starkuk-live-processing-order-papi-v2 | Started | 4 | Business — order processing | High | 4 ENABLED schedulers (order create every 3 min, status every 15 min). Live order flow with NO integration mapping — invisible to any integration-level plan. Map it, then bring into replan or confirm replacement.
sgbd-live-okta-contact-eapi-v1 | Started | 0 | Business — Okta/contact | Medium | Started, unmapped; relates to MUL-OKTA-SYNC (still OPEN in replan). Fold into the OKTA-SYNC decision.
stark-live-stark-hr-azure-storage-sapi-v1 | Started | 0 | Business — HR data | Medium | Started HR->Azure storage flow, unmapped. Confirm owner and whether HR data movement is in Mule-exit scope.
starkuk-live-order-papi-v2 | Started | 0 | Business — order | Medium | Started order API, unmapped. Confirm integration + exit scope.
starkuk-live-pub-order-eapi-v2 | Started | 0 | Business — order | Medium | Started order API, unmapped. Confirm which integration it belongs to and whether it is in exit scope.
starkuk-live-redflag-sapi-v1 | Started | 0 | Business — RedFlag | Medium | Belongs to MUL-REDFLAG (already in replan, Sl 22). Prod mapping shows N/A — fix the mapping so inventory reports stay complete.
starkuk-live-anypoint-splunk-logforwarder | Started | 0 | Platform — logging | Low | Observability/log forwarding. Likely retired with the Mule platform; confirm logging continuity on Azure.
starkuk-live-business-critical-vpn-v1 | Started | 0 | Platform — network | Low | Network/VPN component. Confirm connectivity replacement in target state.
starkuk-live-hx-to-dbm-poc-v1 | Started | 0 | POC | Low | POC app. Confirm it can be decommissioned (not production-critical).
starkuk-live-retarus-email-sapi-v1 | Started | 0 | Platform — email relay | Low | Shared email relay. Confirm whether any migrated integration depends on it.
starkuk-live-tm1-sapi-v1 | Undeployed | 0 | Undeployed | Low | Undeployed — no runtime footprint. Confirm removable.

## Replan_OOS_Validation
Replan Out-of-Scope / Special items - validated against prod reality
The replan explicitly dispositions these. Cross-check: are the "out of scope / undeployed" calls consistent with what is actually running in prod?
Integration | Replan Label | Confirmation trail (Assumptions tab) | Prod Started Apps | Prod Enabled Triggers | Consistency | SA Note
MUL-ACCOUNT-VALIDATION | MUL-ACCOUNT-VALIDATION (undeployed) | (none recorded) | 3 | 0 | CHECK | Labelled "undeployed" but prod shows started apps live. Decision still OPEN (Seb to check with Tristan). Resolve before exit — either bring into plan or confirm decommission.
MUL-OKTA-SYNC | MUL-OKTA-SYNC (to check with Tristan) | (none recorded) | 5 | 0 | CHECK | Decision OPEN (Seb to check with Tristan) and 5 apps live in prod. Resolve scope; also folds in the unmapped okta-contact-eapi app.
MUL-VANSTOCK-PURCHASEORDER | MUL-VANSTOCK-PURCHASEORDER (out of scope) | (none recorded) | 3 | 0 | CHECK | Confirmed "not in use" (Kristian Bates) yet 3 apps show Started in prod. Reconcile: if truly unused, why started? Confirm safe to decommission.
MUL-COLUMBUS-DOCUMENTS | MUL-COLUMBUS-DOCUMENTS (Phase-1/No. 7) | (none recorded) | 1 | 0 | OK | Partly Phase-1, partly under MUL-CONSOLIDATEDINVOICE. Consistent — verify the CONSOLIDATEDINVOICE line fully absorbs the remainder.
MUL-CONSENT | MUL-CONSENT (out of scope) | (none recorded) | 5 | 1 | OK | Confirmed out of scope by Emma. Still live in prod (incl. 1 enabled scheduler) — fine, just ensure decommission owned outside this exit.
MUL-TRIPDATA | MUL-TRIPDATA (out of scope) | (none recorded) | 1 | 0 | OK | Confirmed out of scope (James Allerton). Consistent.
MUL-SWIFT6-TRANSPORT | MUL-SWIFT6-TRANSPORT (out of scope) | (none recorded) | 1 | 0 | OK | Confirmed out of scope (James Allerton). Note swift6 file flow also runs under transport-papi (FLEETWAVE) — ensure that piece is covered.

## Replan_Internal_Gaps
Replan internal completeness & live blockers (from the replan workbook itself)
Not a prod-vs-replan gap, but items inside the replan that will move dates if unresolved. Surfaced so the "clear view" is complete.
Item | Detail | Priority
DB target undecided for items 7–9 | ConsolidatedInvoice, Consxref, Concur cannot be deployed / QA cannot start until the target DB is confirmed (Rob/Lamaan/Shakeel). ~1 week at risk (Assumptions #5). | High
Consumers not yet engaged | Team (Seb & Puneet) yet to talk to integration consumers about moving Mule->Azure and secure confirmation (Assumptions #3). Long-lead dependency. | High
Live blocker: MUL-INVENTORYAUTOMATION (Relex-Icon) | Awaiting Relex-side IP whitelisting and sandbox credentials (Katie James / Andy). Cannot test until resolved (Challenges log, 17/18-Sep, Open-WIP). | High
UAT effort not yet estimated | 13 of 23 in-scope interfaces still show "?" for UAT effort. UAT tester names/estimates are guesstimates (Assumptions #1, #2). Firm these up or the back end of the plan is unreliable. | Medium
Shared developer capacity | Shakeel not 100% allocated; BAU takes priority, risking occasional slippage on his items (Assumptions #4). | Medium
Live blocker: MUL-CustomerValidation | Icon connection issue + WSDL differences → +2 days dev added; shifts subsequent Shakeel tasks (Challenges log, 17-Sep, Open-WIP). | Medium